## Sheet1
The Basement Theatre Team - Issue Log
Issue No | Date Logged | Last Updated | Description of Issue | Issue Owner | Issue Imapct | Issue Raised By | Issue Control | Current Status
1 | 4/08/2015 | 27/08/2015 | Team member Kai will be in China all of summer break. Most of communication tools are banned. | Jozella | Medium | Kai | Look for an alternative communication tool that is legal to use in China. | Closed
2 | 11/08/2015 | 31/08/2015 | Decision whether to use cross-platform tool or to develop natively | David | High | David & Aaron | Research into pros ans cons between the 2. Ask any other groups who are using a cross-platform tool and who are natively developing. | Closed
3 | 20/08/2015 | 2015-08-31 | Client scope is too broad which can cause problems in the future. Team members are concerned. | Jozella | High | All Team members |  | Open
4 | 31/08/2015 | 4/10/2015 | iTicket (third party) have a busy schedule and can be hard to get response from them. | Jozella | Medium | Jozella |  | Open
5 | 31/08/2015 | 2/10/2015 | Our client's third party ticket provider do not have an API | Jozella | Medium | David |  | Open