## 23_07_15
| Meeting Minutes - The Basement Theatre |  |  | Tab Key
Supervisor Meeting
Client Meeting
Location: | WG Building | Cumulative Hours: | 2 |  | Team meeting
Date: | Thursday 23/07/2015
Time | 12pm-2pm
Attendance: | All team members
Agenda Items: | - Get to know other team members
- Discuss the team agreement
- Discuss avaiablity of each team member
Action Items & Responsibility | - Organise a team avaiablity timetable. (Kai)
- Think about ideas for team agreement (All)
- Email supervisor for 1st meeting (Jozella)
Other Notes:

## 26_07_15
Meeting Minutes - The Basement Theatre
Location: | WT Level 1 | Cumulative Hours: | 4
Date: | Sunday 2/07/2015
Time: | 12pm-2pm
Attendance: | All Team Members & Greig
Agenda Items: | - Introductory meeting with Greig (supervisor)
- Work allocation distributed
- Questions were asked about the project proposal
- Checked availability regarding to meetings with Greig
Action Items & Responsibility | - Set up trello board for project planning (David)
- Think of questions to ask at client meeting (All)
- Email client for introductory meeting (Jozella)
- Set up meeting minutes document ( Jozella)
- Allocate team roles (All)
Other Notes:

## 28_07_15
Meeting Minutes - The Basement Theatre
|  | Cumulative Hours: | 5.5
Location: | WG Building
Date: | Tuesday 28/07/2015
Time | 12.30pm-2pm
Attendance: | All team members
Agenda Items: | - Preperation for client meeting
- Collab on questions to ask during client meeting
- Collab on the team agreement
- Sign team agreement
Action Items & Responsibility | - List more questions to ask the client (All)
- Update trello board (David)
Other Notes: | Client meeting - whos doing what
Jozella - Taking notes and asking questions
Kai - recorder, ask questions
Aaron - Listener, ask questions
David - Ask main questions

## 30_07_15
Meeting Minutes - The Basement Theatre
Location: | Q Theatre | Cumulative Hours: | 6.5
Date: | Thursday 30/07/2015
Time | 2pm-3pm
Attendance: | All team members, Greig and Elise(Client)
Agenda Items: | - Introductory meeting with Elise at the Q theatre
- Ask questions about the company, background, the theatre, target audience
Action Items & Responsibility | - Research trans media (All)
- Brainstorm already exsisting mobile applications (All)
- Start proposal (All)
- Consider possible methodologies (David & Aaron)
- Consider application features (All)
Other Notes:

## 4_08_15
Meeting Minutes - The Basement Theatre
Location: | WG Building | Cumulative Hours: | 8.5
Date: | Tuesday 4/08/2015
Time | 12pm-3pm
Attendance: | All team members
Agenda Items: | - Confirm scope
- Share brainstorn ideas of reseach undertaken of exsisting apps
- Decide of what features should be on the app
- Set project proposal ideal deadline
- Allocate project proposal work through trello
Action Items & Responsibility | - Research the Basement Theatre Company (All)
- Start allocated work (All)
- Start communication plan, introduction, scope (Jozella)
- Start project methodology (David)
- Start project roles (David)
- Start cost estimation (Aaron)
- Start Risk management (Kai)
- Start requirements section (David)
- Book proposal time ( Jozella)
- Email Client for a follow up meeting before proposal (Jozella)
- Update trello board
Other Notes:

## 10_08_15
Meeting Minutes - The Basement Theatre
Location: | WT Level 1 | Cumulative Hours: | 9.5
Date: | Monday 10/08/2015
Time | 12pm-1pm
Attendance: | All team members & Greig
Agenda Items: | - Discussed our project proposal draft with Greig
- Feedback received from Greig and slight changes still need to be made
- Went through the project proposal as team to proof read (QA)
Action Items & Responsibility | - Add in schedule ( Jozella )
- Make changes that Greig recommended ( All)
- Add more detail in Quality Assurance ( Kai)
- Adjust Introduction & Scope (Jozella & David)
- Prepare 5 page slideshow for the proposal
- Final proof read of proposal (All)
Other Notes:

## 11_08_15
Meeting Minutes - The Basement Theatre
|  | Cumulative Hours: | 12.5
Location: | Q Theatre
Date: | Tuesday 11/08/2015
Time | 12pm-3.30pm
Attendance: | All team members & Sam (Client)
Agenda Items: | - Additional requirements were added and discussed
- Team meeting after the client meeting (12.30pm-3.30pm)
- Presentation preperation
- Who is saying what
- Made final touches to the proposal
Action Items & Responsibility | - FINAL FINAL proof read of final version of project proposal for the following day (All)
- Prepare for presentation (All)
- Book room for presentation practice (Jozella)
-
Other Notes: | Elise was not able to attend meeting for she is ill, Sam agreed to meet with us instead

## 12_08_15
Meeting Minutes - The Basement Theatre
Location: | WT Level 1 | Cumulative Hours: | 15.5
Date: | Wednesday 18/8/2015
Time | 12pm - 13.30pm
Attendance: | All team members
Agenda Items: | - Final preperation before presentation
- Do actual presentation
Action Items & Responsibility | - Create a requirements document
- Send Elise a copy of the proposal
- Set up a meeting with client to concrete requirements
- Wait for recommendations from markers
- Create Risk and Issue Log
Other Notes: | Passed the proposal!!! :D

## 18_08_15
Meeting Minutes - The Basement Theatre
Location: | WT Level 1 | Cumulative Hours: | 16.5
Date: | Tuesday 18/08/2015
Time | 12pm-1pm
Attendance: | Aaron , Jozella, Kai & Greig
Agenda Items: | - Met with Greig and the rest of the group to discuss the proposal
- Discussed further changes to be made
- Got told to add in gantt chart and add requirements document
- Recommendations are yet to be received from Anne
- Discuss with the group about upskilling
Action Items & Responsibility | - Email Elise for a client meeting (Jozella)
- Start recommendations document
Other Notes:

## 25_08_15
Meeting Minutes - The Basement Theatre
Location: | WA Building | Cumulative Hours: | 17.5
Date: | Tuesday 25/08/2015
Time: | 12pm-1pm
Attendance: | All team members
Agenda Items: | - Review recommendations with the whole team
- Discuss who is fixing/adjusting what in the proposal
- Discuss upskilling swift/xcode
Action Items & Responsibility | - Add tasks on trello board (David)
- Start allocated tasks
- 1. Review your requirement list, check your user groups and make sure that you have a very detailed requirement analysis document and let the client sign it (Kai)
2. Review your schedule and check the duration of items and sprints. Allow enough time for learning new tools (Jozella)
3. Evaluate and select the right technical tool, for example Xamarin is a cross platform for IOS and ANDROID (All, mainly Aaron)
4. You explain the SCRUM principles in general, but your need to apply those principles to your specific project. You should include acceptance tests before you start implementing on page 17 in your SCRUM phase overview, also check your section 4.1.4. (David)
5. Your plan must reflect your methodology! (Jozella)
6. Check your quality assurance activities and make sure that you include activities to deliver high quality work. (Aaron, Kai, David)
Other Notes:

## 31_08_15
Meeting Minutes - The Basement Theatre
Location: | Q Theatre | Cumulative Hours: | 19.5
Date: | Monday 31/08/2015
Time | 2pm - 4pm
Attendance: | David, Jozella Kai, Greig, Sam & Elise
Agenda Items: | - Disscused requirements with Elise and Sam
- Added/Removed some requirements
- Received positive feedback of project proposal from Elise & Sam
- Also expressed our concern about iTicket how they do not have an API
- Team meeting after client meeting about requirements. Table drawn of all requirements, put them in groups
Action Items & Responsibility | - Follow up with Elise to get meeting or skype session with iTicket (Jozella)
- Start user stories and acceptance tests (All, mainly David)
- Start upskilling, going through tutorials on lynda.com and youtube (All)
- Allocate tutorials and tasks on trello for the break (David)
Other Notes:

## 17_09_15
Meeting Minutes - The Basement Theatre
Location: | WT Level 1 | Cumulative Hours: | 20
Date: | Thursday 17/09/2015
Time: | 11am-11.30am
Attendance: | Jozella, Kai & Greig
Agenda Items: | - Welcome back meeting with Greig to see if we are in track
- NEED TO START GANTT CHART!!
- Brief discussion about mid project review
- Received positive feedback from Greig and to keep doing what we are doing
Action Items & Responsibility | - Start Gantt Chart (VERY BEHIND!!!) (Kai)
- Continue with upskilling with swift(All)
- Research Crossplatforming & native mobile development (All)
- Update schedule (Kai & David)
- Email iTicket to arrange meeting or skype session (Jozella)
Other Notes:

## 29_09_15
Meeting Minutes - The Basement Theatre
Location: | WT Level 1
Date: | Tuesday 29/09/2015 | Cumulative Hours: | 21
Time: | 12pm-1pm
Attendance: | All team members
Agenda Items: | - Team meeting about progress on upskilling
- Discussed on ways to install Xcode on PC - through virtual box
- Discussed further whether to cross platform or to natively develop the mobile app
- Also discussed user stories and acceptance tests
- Allocated tasks for mid project review preperation
Action Items & Responsibility | - Update trello board (David)
- Finish last videos of tutorials of swift/xcode (All)
- Gather documents for mid project review (All)
- Send requirements document draft to Greig (Jozella)
- Email Greig to check availability of project review date (Jozella)
- Also need to book session time time for project review!! ( Jozella)
Other Notes:

## 6_10_15
Meeting Minutes - The Basement Theatre
Location: | WT Level 5
Date: | Tuesday 06/10/2015 | Cumulative Hours: | 22.5
Time: | 12pm-1.30pm
Attendance: | All team members
Agenda Items: | - Discuss status report, to see if everyone is on track
- Clarification about what happens in the mid project review
- Discussed again about cross-platforming and native development. Group has decided with native development
- Set a deadline for status report (Wed)
- Played planning poker to see the most difficult tasks
Action Items & Responsibility | - Work on status report which is due on Thursday 8/06/15 (All)
- Prepare documents for mid project reivew (All)
- Prepare screenshots of emails, fb messanger, trello (Jozella)
- Research quality assurance protocols (All)
- Update Risk and issue log (Jozella)
Other Notes: