## Sheet1
The Basement Theatre Team - Risk Log
Risk # | Date Logged | Last Updated | Description of Risk | Risk Owner | Risk Level | Risk Raised By | Risk Control | Current Status
1 | 2015-08-20 | 2015-08-31 | Client has a broad scope. Team members are concerned about the time frame and skillset. | Jozella | Medium | Kai, David | Have a client meeting discussing requirements and possible outcomes and other alternatives if scope is too broad. Also set more time to upskill | Open
2 | 2015-09-18 | 2015-09-08 | Group members not attending team meetings due to illness | Jozella | Medium | Jozella | Have a skype session to explain what the team member has missed. | Closed
3 | 2015-10-01 | 2015-09-12 | Decision made to natively create applicaion rather than cross-platform. Time and cost are to be considered | David | High | Jozella | Commit to a number of hours in the summer break for upskilling in both java and swift. | Open
4
5
6
7
8
9
10
11